## Slide 1: EASTERN & SOUTHERN AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE (ACEII)
AFRICA CENTRE OF EXCELLENCE FOR SUSTAINABLE MINING ACE-SM
THE COPPERBELT UNIVERSITY
ZAMBIA

## Slide 2: ACE Background
KEY DEVELOPMENT CHALLENGES:
Achieve sustainability in mining in terms of better mining practice, health of communities, and effects on biodiversity
VISION:
To be a national, regional and global source of best practice, knowledge and experience in the field of Sustainable Mining.
Project Development Objective:
To strengthen selected Eastern and Southern African higher education institutions to deliver quality post-graduate education and build collaborative research capacity in the regional priority areas.
MISSION:
To focus on delivering excellence in education, training, and research in five thematic areas identified as strategic to improving the sustainability of the mining industry in Zambia and beyond for years to come.

## Slide 3: ACE Management
Vice Chancellor
General Management Committee
ACE-SM Advisory Board
Project Manager
Dean School of Built Environment
Thematic area coordinators
Dean School of Engineering
Dean School of Mines & Mineral Sciences
Dean School of Business
Dean School of Natural Resources
Dean School of Maths & Nat.Sciences
Assistant project manager
Admin Assistant
M& E Officer
ACE-SM Centre Leader
Deputy Centre Leader

## Slide 4: Main Achievements and Highlights in the Last 6 Months
  We received our first students in response to calls for scholarships at PhD and MSc levels.
  We employed our first employee of the Centre who is fully supported by the project in the position of Project Administrative Assistant
  We prepared a promotional video that was well-received at Technical Assistance Meeting (Kigali 2018)
  We raised 22800 USD in externally generated funds from a research grant and application fees
  M&E, Project Management and Risk Assessment Workshops were conducted for Centre Members

## Slide 5: New and/or Revised ACE Ph.D., Master, and Short Term Courses to be developed
A PhD in Sustainable Mining has been developed and is at final stages of approval by CBU Senate.
A comprehensive list of short courses has been developed in conjunction with stakeholders and Schools at CBU. We are now ready to offer short courses in the next quarter.

## Slide 6: ACE Targets & Results Achieved for YEAR 1 (you can use figures and charts to illustrate progress of selected results)
Indicator | Value | Year 1 target | Year 1 actual
Regional students enrolled in ACEs | Masters (Total) | 7 | 8
 | Masters (Female) | 2 | 1
 | PhD (Total) | 2 | 2
 | PhD (Female) | 1 | 0
 | Short-term courses (Total) | 0 | 0
 | Short-term courses (Female) | 0 | 0
Total students (regional and national) enrolled in ACEs | Masters (Total) | 41 | 61
 | Masters (Female) | 15 | 15
 | PhD (Total) | 10 | 3
 | PhD (Female) | 2 | 1
 | Short-term courses (Total) | 100 | 0
 | Short-term courses (Female) | 40 | 0

## Slide 7: ACE Targets & Results Achieved for YEAR 1
Indicator | Value | Year 1 target | Year 1 actual
MOUs on partnerships for collaboration in applied research and training entered into by the ACEs | Total | 5 | 5
Accredited education programs offered by the ACEs | Total | 5 | 0
 | Masters (National accreditation) | 5 | 0
 | Masters (Regional accreditation) | 5 | 0
 | Masters (International accreditation) | 3 | 0
 | PhD (National accreditation) | 0 | 0
 | PhD (Regional accreditation) | 0 | 0
 | PhD (International accreditation) | 0 | 0
Direct Project beneficiaries | Total | 87 | 46
 | Female | 39 | 16
 | Students (Total) | 65 | 64
 | Students (Female) | 17 | 16
 | Faculty (Total) | 10 | 8
 | Faculty (Female) | 5 | 1

## Slide 8: ACE Targets & Results Achieved for YEAR 1
Indicator | Value | Year 1 target | Year 1 actual
Faculty and PhD students exchanges to promote research and teaching | Total | 14 | 8
 | Female | 10 | 1
Amount of externally generated revenue by the ACEs | USD | 48000 | 22800
Internationally recognized research publications in disciplines supported by the ACE Program and with regional coauthors | Total | 20 | 21
 | No. co-authored with regional collaborators | 9 | 6
No. of institutions hosting ACEs participating in the PASET benchmarking exercise | Total | 1 | 1

## Slide 9: IDA FUNDS RECEIVED and UTILIZED
Amount Received | Date | Amount Utilized | Date
USD 1,100,000 | January 2018 | ZMK 377,797.79 (USD37,686.097) | 30 June 2018
 |  | ZMK 256,1655.73 (USD 214,538.14) | 31 December 2018

## Slide 10: PROCUREMENT PROGRESS
Items procured (Works, goods, and consultancies) | Cost | Procurement request submitted on | Current Status
Rehabilitation of Hostels | K420,000 (USD42,000) | May 2018 | In progress. Had to switch from STEP to using CBU system
Purchase vehicle | K600,000 (USD 60,000) | May 2018 | Vehicle delivered November 2018
Rehabilitation of hostels | K420,00 (USD 42,000) | June 2018 | Contractors engaged and to be on site 4th February 2019
External Audit Consultants | To be determined | December 2018 | Bids received and contract to be awarded 8th February 2019
Procurement Audit Consultants | To be determined | December 2018 | Bids received and contract to be awarded 8th February 2019

## Slide 11: Reporting and Compliances
Annual Work Plan status, implementation progress as measured against annual work plan. Progress has been made on the following components of the Annual Work Plan: (Please note, progress measured as: activities done/total activities planned for that component)
  Achieving Learning Excellence (15/44 done)
  Research Excellence (6/23 done)
  Quality assurance (8/22 done)
  Achieving Equity Dimension (1/17 done)
  Attract Academic Staff and Students from the Region (8/14 done)
  National and Regional Academic Partners (7/27 done)
  Collaboration with International Academic Partners (1/5 done)
  Management and Governance (13/21 done)
  Sustainable Financing (5/17 done)
  Monitoring and Evaluation (5/16 done)
Overall: 69/206 outputs achieved as of Feb 2018 (start of our project year) to date.

## Slide 12: Reporting and Compliances
Annual audit report status
  Annual audit report is planned for Quarter1 Year 2 (Feb-Apr 2019)
Procurement audit report status
  2019/2020 Procurement plan submitted
  Procurement Audit to take place Quarter1 Year 2 (Feb-Apr 2019)
Social and environmental safeguards actions and compliance
  Rehabilitation of hostels required Environmental Management Plan submitted previously to be revisited and updated accordingly

## Slide 13: Interim Financial Report status
DATE | EXPENSE | AMOUNT (ZMK)
6.03.18 | Workshop for planning | 43,520.00
10.03.18 | Ibis workshop | 64,668.00
15.03.18 | National Planning meeting Lsk | 2,940.00
23.03.18 | workshop world bank | 12,895.00
11.04.18 | launch meeting at unza | 26,570.00
18.04.18 | Africana Lodge & Restaurant | 1,697.79
19.04.18 | launch lusaka | 92,922.00
24.04.18 | Hired transport ( Rashid ) | 2,000.00
24.04.18 | lunch allowance | 1,185.00
24.04.18 | Airtickets for launch of Ace centre in lsk( omitted ) | 34,404.00
7.05.18 | Techinical & Advisory meeting LSk | 51,330.00
31.05.18 | Accreditation fees | 60,000.00
8.06.18 | Protfolio Review meeting in Lsk | 18,150.00
9.07.18 | Curriculum Development at Chita lodge | 42,020.00
9.07.18 | chita lodge | 48,939.00
13.07.18 | Grant proposal | 27,880.00
16.07.18 | National Steering meeting | 13,400.00
16.07.18 | National Steering meeting | 32,280.00
17.07.18 | National Steering meeting ( allowances) | 8,830.00
20.07.18 | National Steering meeting (tickets) | 2,840.00
16.07.18 | Toyota zambia( purchase of Land cruiser DLX) | 589,625.49
17.07.18 | Ibis gardens Grant proposal( allowances) | 18,889.00
17.07.18 | Ibis gardens Grant proposal | 21,880.00
18.07.18 | Times printpak Zambia | 35,579.52
20.07.18 | Esami ( training) | 30,000.00
20.07.18 | Sentrim 680 hotel( training) | 17,940.00
24.07.18 | Out of pocket ( needs assessments) | 4,150.00
23.07.18 | Training in Kenya DR Mutondo &Dr Chunda | 11,102.00
25.07.18 | Air tickets for travel( training in kenya) | 24,930.00
30.07.18 | Meeting at world bank offices | 23,935.00
7.08.18 | Ibis gardens Grant proposal | 36,327.30
08.08.18 | Grant proposal in ndola | 21,680.00
7.08.18 | Ibis gardens Grant proposal | 36,327.30
08.08.18 | Grant proposal in ndola | 21,680.00
DATE | EXPENSE | AMOUNT (ZMK)
08.08.18 | Project manager allowance | 12,833.83
22.08.18 | Ucon Projects (accomodation in SA) | 5,098.00
22.08.18 | African Traning Institute SA | 47,300.00
22.08.18 | Allowances For Traning Mrs kanga & Mwamba | 11,256.00
29.08.18 | Air tickets for travel( training in South africa) | 19,770.00
05.09.18 | Meeting at Zappa in Lusaka Dr phenny & Miss C Mfula | 13,995.00
05.09.18 | Training allowance Mr Songolo Mwiya | 5,840.60
07.09.18 | Training Guest house SA | 7,889.00
07.09.18 | Air ticket Mr Songolo Mwiya | 8,980.00
07.09.19 | Training at University of Cape town | 7,000.00
11.09.18 | Project manager allowances | 8,000.00
17.09.18 | Petty Cash for project manager | 10,000.00
18.09.18 | Eagle Adventures& Tours( Tickets top up For Mwamba & Mr mwiya) | 3,290.00
27.09.18 | Bersil Enterprises Ltd- (6 Photo copiers) | 129,696.00
8.10.18 | Private registration number fee for vehicle for centre | 500.00
9.10.18 | Briding gap Solutions limited( 2 projector & 2 scanner ) | 22,135.00
10.10.18 | Project Manager allowances | 8,000.00
10.10.18 | M&E workshop at Fringilia Lodge (Staff) | 148,275.00
10.10.18 | M&E workshop at Fringilia Lodge conference faclilities. | 32,250.00
23.10.18 | Ruform in kenya (accomodation & participation fees) | 8,805.00
23.10.18 | DR Gershom Mwandila allowances | 6,634.00
26.10.18 | Airticket for Dr Mwandila | 15,765.00
30.10.18 | Bank charges/ | 3,176.40
30.10.18 | Bank interest USD | (11,126.86)
30.10.18 | Imprest cash repayments | (13,644.61)
5.11.18 | Briding gap Solutions limited( 2 projector & 2 scanner ) | 22,135.00
9.11.18 | Madison Life Insurance Zambia( treavel cover for Dr Chama) | 413.59
9.11.18 | ZNBC | 4,100.00
07.11.18 | Kigali Rwanda Trip( DR mwaanga, Dr Mutondo& Dr Kalaba | 57,183.00
13.11.18 | Eagle Adventures& Tours( Tickets ) | 32,070.00
13.11.18 | Wave -Tech ( purchase of 8 laptops & 1desk top) | 76,270.00
13.11.18 | Allowances Project manager | 8,000.00
14.11.18 | Eskayarts Ltd( 10 desks & 10 Chairs) | 63,270.00
14.11.18 | Team work software | 64,476.00
23.11.18 | Ibis Gardens Ltd( work shop) | 26,354.38
27.11.18 | Gwedolen Nayame ( work shop allowances) | 128,880.00
7.12.18 | Wave -Tech ( purchase of 8 laptops & 1desk top) | 76,270.00
7.12.18 | Allowances Project manager | 8,000.00
Total |  | 2,561,655.73

## Slide 14: Next Steps
Develop Monitoring and Evaluation tools and familiarise Centre members on how to use them for collection of quality data.
Ensure stakeholders receive M & E Reports so they see what happens to data they submit via M & E activities.
Use Risk Register generated from Risk Assessment Workshop to understand and sensitise Centre members on real risks to the Project’s successful completion (and how they can be mitigated).

## Slide 15: Challenges and/or Reflections
Persistent challenges and reflections
  The University community still needs to understand how to participate fully in the project and how the ACE-SM relates to them.

## Slide 16: Areas Where You Need Support from NSC, IUCEA and WB
Capacity building on routine project functions:
  Project Cycle Management
  Monitoring and Evaluation
  Financial Management and Reporting
  Long term stakeholder engagement
  Fundraising
  Communication

## Slide 17: Key Partners (you can add logos; only those who sign formal MOUs and with action plan)